## Sheet1
GCT | (Governance Control Tasks)
Sno | Page List | Assigned To | Target Date | Status | Remarks
1 | Task Master | krishna |  | completed
2 | Document Type | krishna |  | completed
3 | Document Category | krishna |  | completed
4 | Document SubCategory | krishna |  | completed
5 | Authority Type | madhura |  | completed
6 | Authority Name | madhura |  | completed
7 | Nature of Document | madhura |  | completed
8 | Department Master | akhilesh |  | completed
9 | Add Entity , Unit Location Master | bharath |  | completed
10 | User Reponsible Location Mapping | akhilesh |  | completed
11 | Add Document | Vishnu | 2023-12-04 | 80% completed (regarding Implementations still disconetion is going on with Jasmeet sir ) | Completed : Cover PageReport Generation ,Pending : PDF formates of Merging with CoverTemp with Main document to make single document
12 | Saved Draft | madhura |  | pending | currently kept Hold
13 | View Published Document | krishna | 2023-12-01 | pending
14 | Update Published Document | krishna | 2023-12-01 | 90% completed | testing required
15 | Disable Published Document | krishna |  | completed | testing required
16 | Reactivate Published Document | krishna |  | completed | testing required
17 | Version Change Document | madhura | 2023-12-04 | 90%Completed | testing required
18 | Review Status Document | Asha | 2023-12-05 | pending
19 | Provide Access | akhilesh | 2023-12-04 | pending | as today(20-Nov meet) as more changes are added in pages new to plan again
20 | Edit Access | akhilesh | 2023-12-06 | pending
21 | Remove Access | akhilesh | 2023-12-07 | pending
22 | Acknowledgement Requested | Asha,vishnu |  | inprogress | checking with document viewer flow
23 | Document User Accessibility | asha |  | pending
24 | Document Repository |  |  | pending
25 | User Management | akhilesh | 2023-12-01 | 90% completed | Completed : Add user with multi role assigment , Penidng : Edit User and reset Password
26 | Role Master | bharath | 2023-12-01 | 90% completed | Pending : Edit role wise page mapping , Completed : Create Role and Page mapping
27 | FileCategory Master(main , Support file) | bharath,sharanya |  | completed
GCA | (Governance Control Assessment)
Sno | Pending Tasks | Assigned To | Target Date | Status | Remarks
1 | Score Indicators | madhura |  | completed
2 | Competency Skill Levels | madhura |  | completed
3 | Key Improvement Indicators | madhura |  | completed
4 | Assessment Template Attributes(Add Type , Assessment Sub-Type) | krishna |  | completed
5 | Assessment Builder | sharanya(question paper generation logic) , Subharsri ( Latest Ui validations Part) | shubasri(05-12-2023) | pending | meet(27-11-2023) changes added some features to explore in Jam board
6 | Customized Assesment | subharsri | 2023-12-08 | pending
7 | Define Subject | madhura |  | completed
8 | Define Topic | madhura |  | completed
9 | Competency Check Level | krishna |  | completed
10 | Add Question | KRISHNA (UI), sharanya(backend) |  | completed
11 | Edit Questions | sharanya(backend) |  | completed | but need to test
12 | Disable Questions | bharath |  | completed
13 | Reactivate Questions | bharath |  | completed
14 | My Questions | sharanya |  | completed
15 | Question Bank Reserve | sharanya |  | completed
16 | Assessment Templates Provide Access |  |  | pending
17 | Assessment Template Edit Access |  |  | pending
18 | Assessment Template Remove Access |  |  | pending
pending