## Risk-SA(PART-1)
FRS Note on Risk Super Admin Control Tasks (Part 1)_SA | Super Admin (Risk)
Activity Headers | Tasks | Assigned To | % Completion | Estimated Working Days | Start Date | End Date | Status | Notes | Testing Status | QA Person
RSACT-01: Risk Matrix Attributes Default Set Up
1 | Type of Risk | Asha | 100 | 1 | 2024-07-31 | 2024-07-31 | Completed
2 | Risk Classification | Asha | 100 | 1 | 2024-08-01 | 2024-08-01 | Completed
3 | Risk Impact Rating | Madhura | 50 |  | 2024-08-05 |  | Completed
4 | Risk Likelihood of Occurrence Factor | Madhura | 50 |  | 2024-08-05 |  | Completed
5 | Risk Categorization | Madhura | 100 | 1 | 2024-08-08 | 2024-08-08 | Completed
6 | Risk Cause List | Madhura | 100 | 1 | 2024-08-09 | 2024-08-09 | Completed
7 | Risk Priority | Krishna | 80 |  | 2024-08-05 |  | Pending
8 | Potential Business Impact | Krishna | 100 | 1 | 2024-08-12 | 2024-08-12 | Completed
9 | Loss Event Threat Category (L1) | Krishna | 100 | 1 | 2024-08-12 | 2024-08-12 | Completed
10 | Loss Event Threat Category (L2) | Krishna | 100 | 1 | 2024-08-13 | 2024-08-13 | Completed
11 | Loss Event Threat Category (L3) | Krishna | 100 | 1 | 2024-08-13 | 2024-08-13 | Completed
12 | Inherent Risk Rating Level | Krishna
13 | Risk Intensity | Krishna
RSACT-02: Control Matrix Attributes Default Set Up
1 | Nature of Control Performance | Madhura | 100 |  | 2024-08-14 | 2024-08-16 | Completed
2 | Nature of Control Occurrence | Madhura |  |  | 2024-08-14 |  | Completed
3 | Control Level | Madhura | 100 |  | 2024-08-14 | 2024-08-16 | Completed
4 | Frequency of Control Applied | Madhura |  |  | 2024-08-14 |  | Completed
5 | Control Dependencies | Madhura | 100 |  | 2024-08-14 | 2024-08-16 | Completed
6 | Risk Control Effectiveness Rating | Krishna |  |  |  |  | Completed
7 | Control Risk of Assessment | Krishna |  |  | 2024-08-20 |  | Completed
8 | Residual Risk Rating | Krishna |  |  | 2024-08-20 |  | Completed
9 | Control Measure | Krishna | 100 |  | 2024-08-14 | 2024-08-16 | Completed
10 | Control Activity Type | Krishna | 100 |  | 2024-08-14 | 2024-08-16 | Completed
11 | Control Reference Type | Krishna | 100 |  | 2024-08-14 | 2024-08-16 | Completed
RSACT-03: Assessment Control Default Settings
1 | BP Maturity Rating Scale Indicators | Krishna | 100 |  |  |  | Completed
2 | Control Hierarchy Settings | Krishna | 100
3 | Control Assessment Test Attributes | Krishna | 100 |  |  |  | completed
4 | Initial Assessment Impact Factor | Madhura | 100 |  |  |  | completed
5 | Risk Mitigation Decision List | Madhura | 100 |  |  |  | completed
6 | Assessment Control Acceptance Criteria | Madhura | 100 |  |  |  | completed
7 | Control Testing PARAMETERS/ Control RELEVANCE Category | Madhura | 100 |  |  |  | completed
8 | Risk Treatment Decision List | Krishna | 100 |  |  |  | completed
9 | Risk Treatment Decision Matrix | Krishna | 100 |  |  |  | completed
10 | Control Test Decision List | Krishna | 100 |  |  |  | completed
RSACT-04: Mitigation Control Default Settings
1 | Mitigation Action Required | Krishna | 100 | 1 | 2024-08-19 | 2024-08-19 | Completed
2 | Action Priority List | Krishna | 100 | 1 | 2024-08-19 | 2024-08-19 | Completed

## Risk-RA(PART-2)
FRS Note on Risk Admin Control Tasks (Part 2)_RA | Risk Controller/ Client Risk Admin
Activity Headers | Tasks |  | Assigned To | % Completion | Start Date | End Date | Status | Notes | Testing Status | QA Person
RACT-01: Risk Business Function Mapping
1 | Create Risk Business Function Mapping |  | Akhilesh | 100 | 2024-08-12 | 2024-08-12 | Completed
2 | Edit Risk Business Function Mapping |  | Akhilesh | 100 | 2024-08-13 | 2024-08-14 | Completed
3 | View Risk BusinessFunction Mapping |  | Akhilesh | 100 | 2024-08-13 | 2024-08-14 | Completed
RACT-02: Risk Matrix Attributes
1 | Type of Risk |  | Madhura | 100 |  |  | Completed
2 | Risk Classification |  | Madhura | 100 |  |  | Completed
3 | Risk Impact Rating |  | Madhura | 100 |  |  | Completed
4 | Risk Likelihood of Occurrence Factor |  | Madhura | 100 |  |  | Completed
5 | Risk Categorization |  | Madhura | 100 |  |  | Completed
6 | Risk Cause List |  | Madhura | 100 |  |  | Completed
7 | Risk Priority |  | Madhura | 100 |  |  | Completed
8 | Potential Business Impact |  | Madhura | 100 |  |  | Completed
9 | Loss Event Threat Category (L1) |  | Madhura | 100 |  |  | Completed
10 | Loss Event Threat Category (L2) |  | Madhura | 100 |  |  | Completed
11 | Loss Event Threat Category (L3) |  | Madhura | 100 |  |  | Completed
12 | Risk Appetite |  | Madhura | 100 |  |  | Completed
13 | Risk Tolerance |  | Madhura | 100 |  |  | Completed
14 | Inherent Risk Rating Level |  | Madhura | 100 |  |  | Completed
15 | Risk Intensity |  | Madhura | 100 |  |  | Completed
RACT-03: Control Matrix Attributes
1 | Nature of Control Performance |  | Madhura
2 | Nature of Control Occurrence |  | Madhura
3 | Control Level |  | Madhura
4 | Frequency of Control Applied |  | Madhura
5 | Control Dependencies |  | Madhura
6 | Risk Control Effectiveness Rating
7 | Control Risk of Assessment
8 | Residual Risk Rating
9 | Control Measure
10 | Internal Control Component
11 | Internal Control Principles
12 | Control Activity Type
13 | Control Activity Nature
14 | Control Activity Sub-Nature
15 | Control Assertion Check
16 | Control Reference Type
17 | Control Acceptance Benchmark
RACT-04A.1: Assessment Control Settings
1 | BP Maturity Rating Scale Indicators
2 | Control Hierarchy Settings
3 | Control Assessment Test Attributes
4 | Initial Assessment Impact Factor
5 | Risk Mitigation Decision List
6 | Assessment Control Acceptance Criteria
7 | Risk Treatment Decision List
8 | Risk Treatment Decision Matrix
RACT-05A.2: Mitigation Control Settings
1 | Mitigation Action Required
2 | Action Priority List
RACT-06A.3: Management Risk Objectives
1 | Key Focus Areas |  | Akhiesh | 90 | 2024-08-14 | 2024-08-20 | Completed but one fields coming from part 2 is pending(BP Maturity Rating Scale Indicator prt 2)
| View and Update of Key Focus Area |  | Akhiesh | 90 | 2024-08-14 | 2024-08-20 | Completed but one fields coming from part 1 is pending
2 | Overall Risk Appetite & Tolerance |  | Akhiesh | 90 | 2024-08-21 | 2024-08-23 | Completed but one field is pending(Assessment Control Acceptance Criteria: part 2)
| view and Update of Overall Risk Appetite |  | Akhiesh | 90 | 2024-08-21 | 2024-08-23 | Completed but one field is pending
3 | Loss Event Tracker |  | Akhiesh | 100 | 2024-08-26 | 2024-08-28 | completed
| View and Update of Loss event Tracker |  | Akhilesh | 90 | 2024-08-27 | 2024-08-28 | Completed but Pending Check box check in Mapp aditional user
RACT-07B.1.1: Risk Assessment Templates
Assessment Template Attributes
1 | Type |  | Akhilesh | 100 | 2024-08-19 | 2024-08-19 | Completed
2 | Sub-Type |  | Akhilesh | 100 | 2024-08-19 | 2024-08-19 | completed
RACT-07B.1.2: Risk Assessment Templates
Assessment Template Rules
1 | Common Assessment Template Rules |  | Akhilesh |  | 2024-08-29 |  | Inprogess
2 | Specific Assessment Template Rules | TO BE UPDATED LATER
RACT-07B.1.3: Risk Assessment Templates
Sampling Standards
1 | Set Sampling Standards
RACT-08: Risk Question Bank
Question Bank Attributes
1 | Define Key Area |  | Akhilesh | 100 | 2024-08-28 | 2024-08-28 | Completed
2 | Define Sub Key Area |  | Akhilesh | 100 | 2024-08-28 | 2024-08-28 | Completed

## Risk-RA(PART-3)
FRS Note on Risk Control Tasks (Part 3) | Applicable to India Units
Activity Headers | Tasks |  | Assigned To | % Completion | Start Date | End Date | Status | Notes | Testing Status | QA Person
RCT-01: Business Process Mapping
1 | Business Process |  | Asha | 100 |  |  | Completed
2 | Business Sub-Process (L1) |  | Asha | 100 |  |  | Completed
3 | Business Sub-Process (L2) |  | Asha | 100 |  |  | Completed
4 | Business Sub-Process (L3) |  | Asha | 100 |  |  | Completed
RCT-03: Risk Mapping
RCT-03A: Risk Register
1 | Create Risk Document/ Register |  | Asha |  |  |  | InProgress | WAITING for Part -2 Completion
2 | View/ Edit Risk Registe
3 | Disable Risk Register
RCT-03B: Risk Matrix
1 | Create Risk Document | refer RCT-03A.1
2 | View/Update Risk Matrix
3 | Disable Risk Matrix
RCT-03C: Risk Library
1 | Create Risk Statement |  | Asha | 10 | 2024-08-27 |  | Completed
2 | EDIT / VIEW Risk Statement |  | Asha |  |  |  | Completed
3 | Deactivate Risk Statement |  | Asha |  |  |  | Completed
4 | Reactivate Risk Statement |  | Asha |  |  |  | Completed
RCT-05: Control Mapping
RCT-05A: Risk & Control Register
1 | Create Control Document/ Register:
2 | View/ Edit Risk & Control Register
3 | Disable Risk & Control Register
RCT-05B: Risk & Control Matrix
1 | Create Control Document | refer RCT-05A.1
2 | View Control Matrix
3 | Disable Control Matrix
RCT-05C: Control Library
1 | Create Control Statement
2 | Edit Control Statement
3 | Deactivate Control Statement
RCT-06: User Access Mapping
RCT-06A: User Access Mapping
1 | Provide Access
2 | Edit Access
3 | Remove Access
RCT-06B:Risk Documents
1 | View Risk Register/ Document | Follow Process RCT-03A.2.1
2 | Update Risk Register Attributes
3 | Disable Risk Register/ Document | Follow Process RCT-03A.3.3
4 | Reactivate Risk Register/ Document | Follow Process RCT-03A.3.4
5 | Risk Register Versioning | Follow Process RCT-03A.2.2
6 | Risk Register Review Period Status
RCT-06C:Control Documents
1 | View Control Register/ Document | Follow Process RCT-05A.2.1 & RCT-05A.2.2
2 | Update Control Register Attributes
3 | Disable Control Register/ Document | Follow Process RCT-05A.3.2
4 | Reactivate Control Register/ Document | Follow Process RCT-05A.3.4
5 | Control Register Versioning | Follow Process RCT-05A.2.2
6 | Control Register Review Period Status
RCT-07: Risk Document Accessibility
RCT-07A : Risk Matrix | View Risk Matrix
RCT-07B: Risk & Control Matrix | View Risk & Control Matrix: